## Project Overview
PROJECT PLAN & PROGRESS: ENGLISH AI SYSTEM
Personalized High School Graduation Exam Preparation Platform
Project Start Date: | 27/05/2026
Target Completion Date: | 30/06/2026
Total Personnel: | 1
Overall Project Status: | In Progress
Total Tasks | Completed | In Progress | Not Started | Delayed | Overall Progress
7 | 0 | 7 | 0 | 0 | 12.86%
PROGRESS BY PROCESS PHASES
Phase Code | Project Phase | Total Tasks | Tasks Completed | Completion Rate
PHASE 1 | Appearance - UX/UI Design | 4 | 0 | 0%
PHASE 2 | AI Intergaration | 3 | 0 | 0%
|  | 0 | 0 | 0%
|  | 0 | 0 | 0%
|  | 0 | 0 | 0%
|  | 0 | 0 | 0%

## Detailed Plan
DETAILED PROJECT TIMELINE & TASK TRACKING
Phase Code | Task Name | Detailed Description / Deliverables | Assignee | Start Date | End Date | Status | Progress
PHASE 1 | UX/UI Design | Create UX/UI for teacher's page and student's page | Leo Harrison | 27/05/2026 |  | In Progress | 20%
PHASE 1 | UX/UI Design | Add functions (upload file, test assignment, etc) | Leo Harrison | 27/05/2026 |  | In Progress | 10%
PHASE 1 | Result Tracking | Create dashboard for score/process tracking using charts | Leo Harrison | 27/05/2026 |  | In Progress | 10%
PHASE 1 | Result Tracking | Add functions if students finish test without mistakes three times in row, it will change the status to "Resolved" | Leo Harrison | 27/05/2026 |  | In Progress | 10%
PHASE 2 | AI Intergration | Intergrate Groq AI to explain the result of test | Leo Harrison | 27/05/2026 |  | In Progress | 30%
PHASE 2 | AI Intergration | Groq AI analyse process/score and personalizedly gives advice | Leo Harrison | 27/05/2026 |  | In Progress | 0%
PHASE 2 | Personalized Learning Process | Groq AI saves wrong questions and answer to database as general knowledge. For instance, students' wrong answer is Conditional Sentence, AI saves it as the name of mistakes (Conditional Sentences) | Leo Harrison | 27/05/2026 |  | In Progress | 10%